## Sheet1
Date: 04/21/2018 |  |  |  | Matthew Peter, Michael Riess, Jonah Kubath
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Get touch screen to work | 20 | 4 | All | 22 | 90% | Yes
Control Screen size of apps | 20 | 1 | All | 2 | 10% | No
Find embedded browser | 20 | 1 | All | 1 | 10% | No
Date: 04/28/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Get touch screen to work | 0.5 | 4 | Matt | 0.5 | 100% | Yes
Get touch keyboard to work with browser | 6 | 4 | Matt | 3 | 75% | Yes
Test embedded browser | 10 | 1 | Jonah/Matt | 5 | 10% | Yes
Date: 05/05/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Limit features available in standard browser | 20 | 3 | Matt | 12 | 60% | No
Test embedded browser | 20 | 1 | Matt/Michael | 15 | 15% | Yes
Date: 05/12/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Limit features available in standard browser | 20 | 3 | Matt/Michael | 10 | 75% | Yes
Remove user access to side and top bars | 8 | 3 | Matt/Michael | 6 | 100% | Yes
Make windows use correct percentage of screen space | 2 | 2 | Matt/Michael | 2 | 100% | Yes
Continue documentation | 4 | 2 | Jonah | 2 | 70% | No
Date: 05/19/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Limit features available in standard browser | 30 | 3 | Matt | 6 | 90% | No
Date: 05/26/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Limit features available in standard browser | 30 | 3 | Matt | 3 | 100% | No
Date: 06/02/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Compare possible languages for Vending Machine | 4 | 2 | Michael | 4 | 100% | Yes
Date: 06/16/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Add script to implement Firefox Addons | 15 | 2 | Matt | 15 | 100% | No
Date: 06/23/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on base Vending Machine app | 10 | 3 | Michael | 8 | 60% | No
Date: 07/07/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on base Vending Machine app | 10 | 3 | Michael | 4 | 100% | No
Worked on product loading in Vending Machine app | 10 | 3 | Michael | 3 | 20% | No
Date: 07/14/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on product loading in Vending Machine app | 10 | 3 | Michael | 4 | 60% | No
Make graphics for Vending Machine app | 30 | 1 | Matt | 15 | 25% | No
Date: 07/21/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on product loading in Vending Machine app | 10 | 3 | Michael | 6 | 80% | No
Make graphics for Vending Machine app | 30 | 1 | Matt | 10 | 40% | No
Date: 07/28/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on product loading in Vending Machine app | 10 | 3 | Michael | 3 | 100% | No
Make graphics for Vending Machine app | 30 | 1 | Matt | 15 | 60% | No
Date: 08/04/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Make graphics for Vending Machine app | 40 | 1 | Matt | 8 | 75% | No
Date: 08/11/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 30 | 3 | Matt | 10 | 15% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 5 | 80% | No
Date: 08/18/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 30 | 3 | Matt | 10 | 30% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 2 | 85% | No
Date: 08/25/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 40 | 3 | Matt/Michael | 15 | 50% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 1 | 88% | No
Date: 09/01/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 40 | 3 | Matt/Michael | 5 | 60% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 1 | 90% | No
Date: 09/08/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 40 | 3 | Matt/Michael | 5 | 70% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 2 | 93% | No
Date: 09/15/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 40 | 3 | Matt/Michael | 15 | 80% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 1 | 95% | No
Items auto scroll when no user is present | 8 | 1 | Al | 0 | 0% | No
Keep the screen active / awake | 1 | 1 | All | 0 | 0% | No
Set the browser home page to wmich.edu | 1 | 1 | All | 0 | 0% | No
Installation script | 20 | 1 | All | 0 | 0% | No
Add advertisment screen space | 20 | 1 | All | 0 | 0% | No
Build one screen management script | 5 | 1 | All | 0 | 0% | No
Notes:
Met with Asamadu and got feedback on the project. He gave us
advice to move in the direction of having a demo available for the entire
screen so that it can be shown to investors.
Date: 09/22/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 40 | 3 | Matt/Michael | 16 | 85% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 1 | 95% | No
Items auto scroll when no user is present | 8 | 1 | Al | 0 | 0% | No
Keep the screen active / awake | 1 | 1 | All | 0 | 0% | No
Set the browser home page to wmich.edu | 1 | 1 | All | 0 | 100% | Yes
Installation script | 20 | 1 | All | 3 | 25% | No
Add advertisment screen space | 20 | 1 | All | 3 | 50% | No
Build one screen management script | 5 | 1 | All | 3 | 20% | No
Notes:
Met with Asamadu and got feedback on the project.
He liked what we had done so far and took some pictures
of the screen.
Date: 09/29/2018 | Touchscreen Kiosk Interface
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 40 | 3 | Matt/Michael | 25 | 90% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 1 | 95% | Yes
Items auto scroll when no user is present | 8 | 1 | Al | 4 | 90% | Yes
Keep the screen active / awake | 1 | 1 | All | 0.5 | 100% | No
craete installation script | 20 | 1 | All | 6 | 40% | No
Add advertisment screen space | 20 | 1 | All | 15 | 100% | Yes
Build one screen management script | 5 | 1 | All | 3 | 20% | No
Build testing plan | 20 | 3 | Michael | 2 | 100% | Yes
OS testing with Ubuntu 18.04 | 5 | 3 | All | 2 | 60% | No
Notes:
Testing plan - do we need to test physical touch / have
another program send a touch to the dom or is this
handled by electron?
Date: 10/01/2018 | Touchscreen Kiosk Interface
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 40 | 3 | Matt/Michael | 25 | 90% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 1 | 95% | Yes
Items auto scroll when no user is present | 8 | 1 | Al | 4 | 90% | Yes
Keep the screen active / awake | 1 | 1 | All | 0.5 | 100% | No
craete installation script | 20 | 1 | All | 6 | 40% | No
Add advertisment screen space | 20 | 1 | All | 15 | 100% | Yes
Build one screen management script | 5 | 1 | All | 3 | 20% | No
Build testing plan | 20 | 3 | Michael | 2 | 100% | Yes
OS testing with Ubuntu 18.04 | 5 | 3 | All | 2 | 60% | No
Notes:
Testing plan - do we need to test physical touch / have
another program send a touch to the dom or is this
handled by electron?
Date: 10/06/2018 | Touchscreen Kiosk Interface |  |  |  | Matt Peter, Michael Riess, Jonah Kubath
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 40 | 3 | Matt/Michael | 25 | 90% | No | Make more specific
Make graphics for Vending Machine app | 40 | 1 | Matt | 1 | 95% | Yes | More detail
Items auto scroll when no user is present | 8 | 1 | All | 4 | 90% | Yes
create installation script | 20 | 1 | All | 6 | 40% | No
Build one screen management script | 5 | 1 | All | 3 | 20% | No
OS testing with Ubuntu 18.04 | 5 | 3 | All | 2 | 100% | No
Build working test machine | 3 | 1 | Jonah | 3 | 50% | No
Edit touchscreen onboard keyboard to remove certain keys | 1 | 1 | Matt | 0 | 70% | Yes
Edit startup script to run in the proper sequence | 1 | 1 | Matt | 0 | 100% | Yes
Create bootable usb drive with application for testing | 3 | 1 | Jonah | 0.5 | 30% | No
Notes: Met with the client and he has given us a few more features to explore.
Add the option to run a video in the ads section. Possibly mp3
Create a bootable usb drive for him to use to test the application
Add a banner at the top of the screen for location and possibly weather
Add a link in the browser to access the location data from other group's project
Date: 10/13/2018 | Touchscreen Kiosk Interface |  |  |  | Matt Peter, Michael Riess, Jonah Kubath
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 40 | 3 | Matt/Michael | 25 | 100% | Yes
Make graphics for Vending Machine app | 40 | 1 | Matt | 1 | 100% | Yes
Items auto scroll when no user is present | 8 | 1 | All | 4 | 100% | Yes
create installation script | 20 | 1 | All | 10 | 80% | Yes
Build one screen management script | 5 | 1 | All | 4 | 90% | Yes
Build working test machine | 3 | 1 | Jonah | 3 | 100% | Yes
Edit touchscreen onboard keyboard to remove certain keys | 1 | 1 | Matt | 2 | 100% | Yes
Create bootable usb drive with application for testing | 3 | 1 | Jonah | 4 | 100% | Yes
Changed advertisements to resize pictures dynamically to fit the screen | 1 | 1 | Matt | 0.5 | 100% | No
Tested OS setup script | 2 | 1 | Matt/Jonah | 2 | 100% | Yes
Tested Firefox Addon script | 1 | 1 | Matt/Jonah | 0.5 | 100% | Yes
Write unit tests for Angular | 10 | 1 | Michael | 6 | 50% | No
Write unit tests for Electron | 10 | 1 | Michael | 1 | 5% | No
Test browser wth JavaScript | 3 | 1 | Jonah | 0 | 0% | No
Updates: set_xinput_matrix.sh fails when Touch Screen is not found
setWindowSizes.sh failed
Notes: Met with the client to give him the bootable USB drive
Met again with the client. He has requested that we set up another USB drive.
The first USB drive was for testing the application and changing advertisements.
The second USB drive will contain the entire project at the current state for
demonstration.