## Sheet1
Project: Touchscreen Kiosk Interface
Description: A large touchscreen has been purchased to be used as an interface for customers. The screen will |  |  | Web Browser
be divided into 3 sections for the customer. The top section will be a web browser. This browser
will have features disabled to limit what resources on the computer the customer can access. These limitations
include: limited open tables, cannot close the window, cannot fullscreen videos, cannot save documents. |  |  | Vending App
The second and third portion will both be controlled by the same application, but will have different
functionality. The second portion will be the interface to the vending machine. Customers will be |  |  | Advertisements
able to view and purchase items sold in the vending machine. The vending app is very minimalistic
as to not require technology knowledge to operate / use it.
The third and final section is dedicated to advertisements. This section will scroll through pictures
that are located in the src directory of the project. In the first version of the application, only pictures
are supported for the advertisements, but the sponsor would like to see video capabilities as well.
Version 1 - The thought behind version one of the Touchscreen Kiosk Interace is to get a basic working
design and application. This will satisfy most of the sponsor's wishes on features. A good amount of time
will be spent on how to work with the touchscreen hardware to limit features accessible to the user.
The other time will be used to build the application and modify the browser.
Version 2 - At this stage, the basic vending application will have been created and tested. Version 2
will allow for nearly all the time to be spent on upgrading the vending app or changing the browser.
The work with the hardware should be essentially complete. Version 2 would like to include a database
for managing multiple devices, web interface to adjusting advertisment images, support for videos
on advertisements, and other features.
.-----------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------
Touchscreen Kiosk Interface
Matt Peter, Michael Riess, Jonah Kubath
09/29/2018 Stories Table
Story | Time Estimate (Hrs) | Risk(1-5) | Total Time (Hrs) | % Complete
The customer can use internet browser, in a limited capacity to increase security | 20 | 3 | 10 | 90%
The customer can view the available products in the vending machine | 50 | 1 | 30 | 90%
The customer can purhcase products in the vending machine | 20 | 4 | 10 | 50%
The customer receives a confirmation of their purchase | 5 | 1 | 0 | 0%
The customer can transfer electronic money via credit / debit card | 100 | 5 | 0 | 0%
Ads that are displayed on the screen on the Ad Window | 15 | 1 | 3 | 75%
When no customer is using the machine, products automatically scroll to display | 10 | 1 | 0 | 0%
The admins can change advertisement and product data remotely | 40 | 3 | 20 | 40%
Release 2-----------------------------------
Touchscreen Kiosk Interface
Matt Peter, Michael Riess, Jonah Kubath
10/08/2018 Stories Table
Story | Time Estimate (Hrs) | Risk(1-5) | Total Time (Hrs) | % Complete
The customer can use internet browser, in a limited capacity to increase security | 20 | 3 | 10 | 90%
The customer can view the available products in the vending machine | 50 | 1 | 30 | 90%
The customer can purhcase products in the vending machine | 20 | 4 | 10 | 50%
Ads that are displayed on the screen on the Ad Window | 15 | 1 | 3 | 75%
When no customer is using the machine, products automatically scroll to display | 10 | 1 | 6 | 100%
The admins can change advertisement and product data remotely | 40 | 3 | 20 | 40%
Create a popup / confirmation page for purchases | 6 | 2 | 0 | 0%
Create installation documentation | 4 | 1 | 0 | 0%
Create app documentation for devs to make changes | 8 | 1 | 0 | 0%
Implement Let's encrypt for security | 4 | 3 | 0 | 0%
Create script to turn off processes that are not necessary to the project | 2 | 1 | 0 | 0%
Only enable ssh connections into the computer | 1 | 1 | 0 | 0%
Release 2-----------------------------------
Create database / web interface to hold and manage kiosk information
Create database to use for updating advertisements
Add support for e-currency (add money to a card or transfer money) | 100 | 5 | 0 | 0%
Create allerting feature to send a message when quantities become low
IT?
Admin | modify the vending machine
Advertisers
Quantitiy falls below a cutoff - notify someone
Add popup for purchase confirmation
Name for e-currency
Security - interface works properly, someone hacks in, dispenses free items
Configure computer to only allow ssh
Let's encrypt to run
Ubuntu secure / disable services
Ansible to configure the computer