## Sheet1
Date: 04/21/2018 |  |  |  | Matthew Peter, Michael Riess, Jonah Kubath
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Get touch screen to work | 20 | 4 | All | 22 | 90% | Yes
Control Screen size of apps | 20 | 1 | All | 2 | 10% | No
Find embedded browser | 20 | 1 | All | 1 | 10% | No
Date: 04/28/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Get touch screen to work | 0.5 | 4 | Matt | 0.5 | 100% | Yes
Get touch keyboard to work with browser | 6 | 4 | Matt | 3 | 75% | Yes
Test embedded browser | 10 | 1 | Jonah/Matt | 5 | 10% | Yes
Date: 05/05/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Limit features available in standard browser | 20 | 3 | Matt | 12 | 60% | No
Test embedded browser | 20 | 1 | Matt/Michael | 15 | 15% | Yes
Date: 05/12/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Limit features available in standard browser | 20 | 3 | Matt/Michael | 10 | 75% | Yes
Remove user access to side and top bars | 8 | 3 | Matt/Michael | 6 | 100% | Yes
Make windows use correct percentage of screen space | 2 | 2 | Matt/Michael | 2 | 100% | Yes
Continue documentation | 4 | 2 | Jonah | 2 | 70% | No
Date: 05/19/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Limit features available in standard browser | 30 | 3 | Matt | 6 | 90% | No
Date: 05/26/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Limit features available in standard browser | 30 | 3 | Matt | 3 | 100% | No
Date: 06/02/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Compare possible languages for Vending Machine | 4 | 2 | Michael | 4 | 100% | Yes
Date: 06/16/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Add script to implement Firefox Addons | 15 | 2 | Matt | 15 | 100% | No
Date: 06/23/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on base Vending Machine app | 10 | 3 | Michael | 8 | 60% | No
Date: 07/07/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on base Vending Machine app | 10 | 3 | Michael | 4 | 100% | No
Worked on product loading in Vending Machine app | 10 | 3 | Michael | 3 | 20% | No
Date: 07/14/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on product loading in Vending Machine app | 10 | 3 | Michael | 4 | 60% | No
Make graphics for Vending Machine app | 30 | 1 | Matt | 15 | 25% | No
Date: 07/21/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on product loading in Vending Machine app | 10 | 3 | Michael | 6 | 80% | No
Make graphics for Vending Machine app | 30 | 1 | Matt | 10 | 40% | No
Date: 07/28/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on product loading in Vending Machine app | 10 | 3 | Michael | 3 | 100% | No
Make graphics for Vending Machine app | 30 | 1 | Matt | 15 | 60% | No
Date: 08/04/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Make graphics for Vending Machine app | 40 | 1 | Matt | 8 | 75% | No
Date: 08/11/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 30 | 3 | Matt | 10 | 15% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 5 | 80% | No
Date: 08/18/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 30 | 3 | Matt | 10 | 30% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 2 | 85% | No
Date: 08/25/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 40 | 3 | Matt/Michael | 15 | 50% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 1 | 88% | No
Date: 09/01/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 40 | 3 | Matt/Michael | 5 | 60% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 1 | 90% | No
Date: 09/08/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 40 | 3 | Matt/Michael | 5 | 70% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 2 | 93% | No
Date: 09/15/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 40 | 3 | Matt/Michael | 15 | 80% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 1 | 95% | No
Items auto scroll when no user is present | 8 | 1 | Al | 0 | 0% | No
Keep the screen active / awake | 1 | 1 | All | 0 | 0% | No
Set the browser home page to wmich.edu | 1 | 1 | All | 0 | 0% | No
Installation script | 20 | 1 | All | 0 | 0% | No
Add advertisment screen space | 20 | 1 | All | 0 | 0% | No
Build one screen management script | 5 | 1 | All | 0 | 0% | No
Notes:
Met with Asamadu and got feedback on the project. He gave us
advice to move in the direction of having a demo available for the entire
screen so that it can be shown to investors.
Date: 09/22/2018
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 40 | 3 | Matt/Michael | 16 | 85% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 1 | 95% | No
Items auto scroll when no user is present | 8 | 1 | Al | 0 | 0% | No
Keep the screen active / awake | 1 | 1 | All | 0 | 0% | No
Set the browser home page to wmich.edu | 1 | 1 | All | 0 | 100% | Yes
Installation script | 20 | 1 | All | 3 | 25% | No
Add advertisment screen space | 20 | 1 | All | 3 | 50% | No
Build one screen management script | 5 | 1 | All | 3 | 20% | No
Notes:
Met with Asamadu and got feedback on the project.
He liked what we had done so far and took some pictures
of the screen.
Date: 09/29/2018 | Touchscreen Kiosk Interface
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 40 | 3 | Matt/Michael | 25 | 90% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 1 | 95% | Yes
Items auto scroll when no user is present | 8 | 1 | Al | 4 | 90% | Yes
Keep the screen active / awake | 1 | 1 | All | 0.5 | 100% | No
craete installation script | 20 | 1 | All | 6 | 40% | No
Add advertisment screen space | 20 | 1 | All | 15 | 100% | Yes
Build one screen management script | 5 | 1 | All | 3 | 20% | No
Build testing plan | 20 | 3 | Michael | 2 | 100% | Yes
OS testing with Ubuntu 18.04 | 5 | 3 | All | 2 | 60% | No
Notes:
Testing plan - do we need to test physical touch / have
another program send a touch to the dom or is this
handled by electron?
Date: 10/01/2018 | Touchscreen Kiosk Interface
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 40 | 3 | Matt/Michael | 25 | 90% | No
Make graphics for Vending Machine app | 40 | 1 | Matt | 1 | 95% | Yes
Items auto scroll when no user is present | 8 | 1 | Al | 4 | 90% | Yes
Keep the screen active / awake | 1 | 1 | All | 0.5 | 100% | No
craete installation script | 20 | 1 | All | 6 | 40% | No
Add advertisment screen space | 20 | 1 | All | 15 | 100% | Yes
Build one screen management script | 5 | 1 | All | 3 | 20% | No
Build testing plan | 20 | 3 | Michael | 2 | 100% | Yes
OS testing with Ubuntu 18.04 | 5 | 3 | All | 2 | 60% | No
Notes:
Testing plan - do we need to test physical touch / have
another program send a touch to the dom or is this
handled by electron?
Date: 10/06/2018 | Touchscreen Kiosk Interface |  |  |  | Matt Peter, Michael Riess, Jonah Kubath
TPS
Task | Time Est (Hrs) | Risk | Who | Time Spent (Hrs) | % Complete | Peer Review
Worked on programming of Vending Machine app | 40 | 3 | Matt/Michael | 25 | 90% | No | Make more specific
Make graphics for Vending Machine app | 40 | 1 | Matt | 1 | 95% | Yes | More detail
Items auto scroll when no user is present | 8 | 1 | All | 4 | 90% | Yes
create installation script | 20 | 1 | All | 6 | 40% | No
Build one screen management script | 5 | 1 | All | 3 | 20% | No
OS testing with Ubuntu 18.04 | 5 | 3 | All | 2 | 100% | No
Build working test machine | 3 | 1 | Jonah | 3 | 50% | No
Edit touchscreen onboard keyboard to remove certain keys | 1 | 1 | Matt | 0 | 70% | Yes
Edit startup script to run in the proper sequence | 1 | 1 | Matt | 0 | 100% | Yes
Notes: